## How to use
FREE TEMPLATE
FF&E schedule with order-by dates
One line per item. Give each line a lead time and an install date and the sheet works out the last day you can order it, how many days are left, and whether it is OK, at risk, late or blocked.
Getting started
1. Clear the sample | The first 30 rows on Schedule (shaded Ref cells) are fictional examples, and so are the rooms and suppliers. Select the white cells of those rows and press Delete; the formulas stay in place.
2. Set up Lists | On Lists, replace the example exchange rates with today's rates and note the rate date. Check the three settings: default buffer (7 days), default approval buffer (0 days) and the at-risk window (14 days).
3. Add rooms and suppliers | Type your rooms on Rooms and your suppliers on Suppliers. They become the dropdowns on Schedule and drive the totals on those sheets.
4. Fill in the schedule | White cells are for typing. Shaded (brass-headed) columns calculate and are locked. 200 rows are ready; to add more, unprotect the sheet and copy the last row down.
5. Keep status current | Change Status as items move from Specified to Installed. Anything Ordered or beyond drops out of the risk count; On hold and Out of stock show as Blocked.
How the dates work
Order-by date | Install date − Buffer (days) − Lead time (weeks) × 7 − Approval buffer (days), rounded down to a whole day. A blank Buffer or Approval buffer uses the default on Lists.
Days until order-by | Order-by date minus today. Negative means the date has passed.
Risk | Blocked if Status is On hold or Out of stock. OK if the item is already Ordered, In production, Shipped, Delivered or Installed. Otherwise Late if the order-by date has passed, At risk if it is within the at-risk window (14 days by default), and OK if not. Needs dates means the lead time or install date is missing.
Buffer | Days between delivery and install: booking the delivery, checking for damage, snagging. Use a larger buffer for items that feed another trade, such as fabric going to an upholsterer (see sample row DR-02).
Approval buffer | Days the client needs to sign off before you can place the order. Set it to 0 once approved.
Sample dates | Sample install and approval dates are formulas relative to today so the risk column shows a realistic mix whenever you open the file. Type real dates over them.
Money
Currency | Enter Unit cost in the supplier's currency and pick the currency. Unit cost (GBP) converts using the rate table on Lists (GBP per one unit of the currency). A currency not on the list turns red.
Line total | Qty × Unit cost (GBP), ex VAT. The header shows totals ex VAT, VAT and inc VAT.
VAT rate | Pick the rate the supplier will charge from the list on Lists. For orders from overseas, check import VAT and duty with your accountant or shipping agent; this sheet does not calculate them.
Rooms and Suppliers | Room and supplier totals use SUMIFS over the schedule, plus counts of late, at-risk and not-yet-ordered lines and the next order-by date for each. A check line flags schedule rows whose room or supplier is not listed, so nothing falls out of the totals unnoticed.
Colour key
Late / Blocked | Order now, or unblock the item (choose an alternative, chase the client).
At risk | The order-by date is inside the at-risk window.
OK | Ordered already, or comfortably ahead of the order-by date.
White cell | Type here.
Shaded cell | Calculated. Locked so formulas are not overwritten by accident.
Good to know
Protection | Sheets are protected without a password so formulas survive busy weeks. To change a formula or sort the whole table, use Review > Unprotect Sheet. Filters work while protected.
Printing | Schedule prints landscape on A4, fitted to the page width, with the header row repeated on every page.
Named ranges | Formulas use named ranges (Sched_Room, Sched_LineGBP, FX_Rate, NudgeDays and so on). See Formulas > Name Manager.
Compatibility | Built for Microsoft Excel 2019 or Microsoft 365. The 'Next order-by' columns on Rooms and Suppliers use MINIFS, which Excel 2016 and earlier do not support; everything else works in older versions.
Made by Techstyles · techstyles.ai
Techstyles does this scoring automatically for every FF&E line, alongside purchase orders, client approvals and Xero. The template works on its own.

## Schedule
FF&E schedule |  |  |  | ORDER-BY DATES · RISK · ROOM AND SUPPLIER TOTALS
Project | [Project name] |  |  | Total ex VAT (GBP) |  | VAT |  | Inc VAT
Today |  | Risk updates every time the file opens. |  | Blocked / late |  | At risk |  | OK
SAMPLE DATA: the first 30 rows (shaded Ref) are fictional examples. Type over them or delete their contents. White cells are for typing; shaded columns calculate and are protected (Review > Unprotect Sheet, no password).
Ref | Room | Item | Description / finish | Supplier | Supplier ref / SKU | Qty | Unit cost | Currency | Unit cost (GBP) | Line total (GBP, ex VAT) | VAT rate | Lead time (weeks) | Install date | Buffer (days) | Approval buffer (days) | Order-by date | Days until order-by | Risk | Status | Client approved | PO number | Notes
EH-01 | Entrance hall | Console table | Fumed oak, hand-waxed, 1600 × 400 × 820 mm | Marlow Joinery Workshop | MJW-CT-1600 | 1 | 2850 | GBP |  |  | 20% | 8 |  |  | 0 |  |  |  | Approved |  |  | Sample. Bespoke. Shop drawings signed off; not yet ordered.
EH-02 | Entrance hall | Pendant light | Hand-blown glass, aged brass gallery, Ø450 mm | Atelier Morvan | AM-PL-450 | 1 | 1980 | EUR |  |  | 20% | 12 |  |  | 0 |  |  |  | In production |  | PO-1001 | Sample. Electrician to confirm ceiling rose position.
EH-03 | Entrance hall | Stair runner | Flatweave wool, 900 mm wide × 4.2 m, custom length | Halvard Textil | HT-RN-0942 | 1 | 18500 | SEK |  |  | 20% | 6 |  |  | 0 |  |  |  | Ordered |  | PO-1002 | Sample. Fitter booked for install week.
EH-04 | Entrance hall | Mirror | Antique giltwood overmantel, approx. 1100 × 1400 mm | Thornbury Antiques | TA-1187 | 1 | 1450 | GBP |  |  | 20% | 0 |  |  | 0 |  |  |  | Delivered |  | PO-1007 | Sample. Held at dealer's store until install.
DR-01 | Drawing room | Three-seat sofa | COM in Ashcombe 'Linden' bouclé, oatmeal; feather-wrapped seat, 2300 mm | Hartwell & Rowe Upholstery | HR-SF-3S-2300 | 1 | 6400 | GBP |  |  | 20% | 10 |  |  | 10 |  |  |  | Awaiting approval |  |  | Sample. Client reviewing fabric sample.
DR-02 | Drawing room | Sofa fabric (COM) | 'Linden' wool bouclé, oatmeal, 14 m | Ashcombe Weavers | AW-LIN-OAT | 14 | 68 | GBP |  |  | 20% | 3 |  | 77 | 0 |  |  |  | Approved |  |  | Sample. Buffer covers the sofa's 10-week build so fabric reaches the upholsterer first.
DR-03 | Drawing room | Armchairs | Walnut frame, saddle leather, cognac | Casa Ferrante | CF-AR-220 | 2 | 3150 | EUR |  |  | 20% | 14 |  |  | 0 |  |  |  | Specified |  |  | Sample. Quote valid 30 days.
DR-04 | Drawing room | Coffee table | Honed travertine top, 1200 × 700 mm | Fenwick Stone & Tile | FST-CT-1270 | 1 | 2200 | GBP |  |  | 20% | 6 |  |  | 0 |  |  |  | Approved |  |  | Sample.
DR-05 | Drawing room | Table lamps (pair) | Glazed stoneware, celadon; linen drum shade | Mesa Clayworks | MC-TL-18 | 2 | 640 | USD |  |  | 20% | 8 |  |  | 0 |  |  |  | Out of stock |  |  | Sample. Supplier awaiting glaze batch; alternative requested.
DR-06 | Drawing room | Rug | Hand-knotted wool, 3000 × 4000 mm | Halvard Textil | HT-HK-3040 | 1 | 74000 | SEK |  |  | 20% | 16 |  |  | 7 |  |  |  | Awaiting approval |  |  | Sample. Strike-off due back from weaver.
DR-07 | Drawing room | Curtains | Made to measure, triple pinch pleat, interlined; 2 pairs | Hartwell & Rowe Upholstery | HR-CU-TPP | 2 | 1850 | GBP |  |  | 20% | 6 |  |  | 0 |  |  |  | Specified |  |  | Sample. Final measure after plastering.
KT-01 | Kitchen | Bar stools | Oak frame, rush seat, 750 mm seat height | Casa Ferrante | CF-BS-75 | 4 | 690 | EUR |  |  | 20% | 10 |  |  | 0 |  |  |  | Shipped |  | PO-1003 | Sample. Tracking received; delivery to site.
KT-02 | Kitchen | Island pendants | Opal glass, Ø300 mm | Lysgaard Studio | LS-OP-300 | 3 | 2400 | DKK |  |  | 20% | 8 |  |  | 0 |  |  |  | Ordered |  | PO-1004 | Sample.
KT-03 | Kitchen | Cabinet handles | Unlacquered brass bar pull, 160 mm centres | Ostrander Brass Co. | OB-PL-160 | 24 | 38 | USD |  |  | 20% | 10 |  |  | 0 |  |  |  | Approved |  |  | Sample. Joiner needs handles before final fit.
KT-04 | Kitchen | Splashback tiles | Glazed handmade tile, 100 × 100 mm, chalk (m²) | Fenwick Stone & Tile | FST-ZL-CH | 6 | 145 | GBP |  |  | 20% | 4 |  |  | 0 |  |  |  | Approved |  |  | Sample. Order 10% overage for cuts.
DN-01 | Dining room | Dining table | Extending, ebonised oak, 2200–3000 mm | Marlow Joinery Workshop | MJW-DT-2230 | 1 | 5600 | GBP |  |  | 20% | 10 |  |  | 0 |  |  |  | Approved |  |  | Sample.
DN-02 | Dining room | Dining chairs | Upholstered seat in client's own fabric | Casa Ferrante | CF-DC-48 | 8 | 540 | EUR |  |  | 20% | 14 |  |  | 0 |  |  |  | In production |  | PO-1005 | Sample. Fabric dispatched to factory.
DN-03 | Dining room | Chandelier | Brass and alabaster, 8-arm, Ø900 mm | Atelier Morvan | AM-CH-8A | 1 | 7400 | EUR |  |  | 20% | 12 |  |  | 5 |  |  |  | Awaiting approval |  |  | Sample. Structural engineer to confirm ceiling load.
DN-04 | Dining room | Sideboard | Antique mahogany, approx. 1850 mm | Thornbury Antiques | TA-1203 | 1 | 3800 | GBP |  |  | 20% | 1 |  |  | 0 |  |  |  | On hold |  |  | Sample. Client deciding between two pieces.
PB-01 | Principal bedroom | Bed | Upholstered headboard, super king 1800 × 2000 mm | Hartwell & Rowe Upholstery | HR-BD-SK | 1 | 4200 | GBP |  |  | 20% | 10 |  |  | 0 |  |  |  | Specified |  |  | Sample.
PB-02 | Principal bedroom | Bedside tables | Lacquered ash, one drawer | Marlow Joinery Workshop | MJW-BS-02 | 2 | 1350 | GBP |  |  | 20% | 8 |  |  | 0 |  |  |  | Specified |  |  | Sample.
PB-03 | Principal bedroom | Wall lights | Plaster uplighter, paintable | Lysgaard Studio | LS-WL-PL | 4 | 1650 | DKK |  |  | 20% | 8 |  |  | 0 |  |  |  | Approved |  |  | Sample. First fix wiring positions issued.
PB-04 | Principal bedroom | Wallpaper | Hand-printed, 10 m rolls | Pell & Hart Papers | PH-HP-210 | 9 | 165 | GBP |  |  | 20% | 5 |  |  | 0 |  |  |  | Specified |  |  | Sample. Decorator hangs before furniture arrives.
PB-05 | Principal bedroom | Rug | Wool and silk, 2500 × 3000 mm | Halvard Textil | HT-WS-2530 | 1 | 39000 | SEK |  |  | 20% | 14 |  |  | 7 |  |  |  | Awaiting approval |  |  | Sample.
BA-01 | Principal bathroom | Freestanding bath | Cast iron, 1700 mm, painted exterior | Kittle Bathrooms | KB-FB-1700 | 1 | 3950 | GBP |  |  | 20% | 6 |  |  | 0 |  |  |  | Delivered |  | PO-1008 | Sample. Four-person lift; booked.
BA-02 | Principal bathroom | Basin taps | Unlacquered brass, three-hole deck mounted | Ostrander Brass Co. | OB-BT-3H | 2 | 820 | USD |  |  | 20% | 10 |  |  | 0 |  |  |  | Ordered |  | PO-1006 | Sample. Plumber to confirm fittings before install.
BA-03 | Principal bathroom | Floor tiles | Honed limestone, 600 × 400 mm (m²) | Fenwick Stone & Tile | FST-LS-6040 | 12 | 118 | GBP |  |  | 20% | 4 |  |  | 0 |  |  |  | Installed |  | PO-1009 | Sample.
GB-01 | Guest bedroom | Bed | Upholstered, king 1500 × 2000 mm | Hartwell & Rowe Upholstery | HR-BD-K | 1 | 2900 | GBP |  |  | 20% | 10 |  |  | 0 |  |  |  | Specified |  |  | Sample.
GB-02 | Guest bedroom | Table lamp | Stoneware, oxblood glaze | Mesa Clayworks | MC-TL-22 | 1 | 480 | USD |  |  | 20% | 8 |  |  | 0 |  |  |  | Specified |  |  | Sample.
ST-01 | Study | Desk | Walnut, leather inset, 1500 × 750 mm | Casa Ferrante | CF-DK-1575 | 1 | 4100 | EUR |  |  | 20% | 14 |  |  | 0 |  |  |  | Specified |  |  | Sample.
Formulas:
Days until order-by = IF([Order-by date]="","",[Order-by date]-TODAY())

## Rooms
Room summary
List the project's rooms in column A; they feed the Room dropdown on the Schedule. Totals are in GBP, ex VAT unless stated, and include sample rows until you clear them.
Room | Level / notes | Items | Ordered | Total ex VAT (GBP) | VAT (GBP) | Total inc VAT (GBP) | Blocked / late | At risk | Next order-by (not yet ordered)
Entrance hall | Ground
Drawing room | Ground
Kitchen | Ground
Dining room | Ground
Principal bedroom | First
Principal bathroom | First
Guest bedroom | Second
Study | Second
Total
Check: schedule lines with a room not listed above
Check: room total matches schedule total

## Suppliers
Supplier summary
List suppliers in column A; they feed the Supplier dropdown on the Schedule. Spend in supplier currency counts only lines priced in the currency shown in column C.
Supplier | Country | Currency | Contact | Email | Typical lead time (weeks) | Account / terms notes | Lines | Not yet ordered | Spend ex VAT (GBP) | Spend ex VAT (supplier currency) | Blocked / late | At risk | Next order-by (not yet ordered)
Hartwell & Rowe Upholstery | UK | GBP | Sales desk | orders@hartwell-rowe.example.com | 10 | 50% deposit, balance before dispatch
Ashcombe Weavers | UK | GBP | Trade desk | trade@ashcombe.example.com | 3 | Trade account, 30 days
Marlow Joinery Workshop | UK | GBP | Workshop | studio@marlowjoinery.example.com | 8 | Shop drawings before production
Fenwick Stone & Tile | UK | GBP | Trade desk | trade@fenwickstone.example.com | 4 | Order 10% overage
Pell & Hart Papers | UK | GBP | Orders | orders@pellhart.example.com | 5 | Batch numbers on delivery note
Thornbury Antiques | UK | GBP | Dealer | hello@thornbury.example.com | 1 | Paid in full to reserve
Kittle Bathrooms | UK | GBP | Trade desk | trade@kittle.example.com | 6 | Kerbside delivery only
Atelier Morvan | France | EUR | Export | export@morvan.example.com | 12 | Pro forma; ex works
Casa Ferrante | Italy | EUR | Export | export@casaferrante.example.com | 14 | 30% deposit; ex works
Lysgaard Studio | Denmark | DKK | Sales | sales@lysgaard.example.com | 8
Halvard Textil | Sweden | SEK | Studio | studio@halvard.example.com | 14 | Strike-off before weaving
Ostrander Brass Co. | USA | USD | Trade | trade@ostrander.example.com | 10 | Prepay; freight quoted separately
Mesa Clayworks | USA | USD | Studio | studio@mesaclay.example.com | 8 | Glaze varies by batch
Total
Check: schedule lines with a supplier not listed above
Supplier names and emails above are fictional sample data (example.com addresses).

## Lists
Lists and settings
Edit the white cells. Everything else in the workbook reads from here.
Status | Counts as ordered | Currency | GBP per 1 unit | VAT rate | Setting | Value
Specified | Ordered | GBP | 1 | 20% | Default buffer (days) when the Buffer cell is blank | 7
Awaiting approval | In production | EUR | 0.85 | 5% | Default approval buffer (days) when blank | 0
Approved | Shipped | USD | 0.75 | 0% | At-risk window: flag items whose order-by date is this many days away or fewer | 14
Ordered | Delivered | DKK | 0.114
In production | Installed | SEK | 0.072 |  | Buffer = days between delivery and install (site access, checking, snagging).
Shipped |  | CHF | 0.93 |  | Approval buffer = days the client needs to sign off before you can order.
Delivered | Items in these statuses are never Late or At risk. Status names are fixed because the Risk formula uses them.
Installed
On hold
Out of stock
Rate date
Example rates only. Replace them with today's rates before you rely on the GBP columns. Add currencies in the empty rows.